## Estimate
Store Shield - Estimate
Feature | Sub-feature | Description | Hours
1. Setup |  |  | 5
| Create app | Make the Shopify app and run it | 2
| Database | Tables to save all data | 1.5
| Default settings | Starting scores and limits | 0.5
| Test store | Sample products and test payments | 1
2. Bot Check |  |  | 13.5
| Visitor script | Small script on every store page | 2
| Browser check | Spot automated browsers | 1.5
| Behaviour check | Mouse, clicks, speed, typing | 2
| Bot score | Add up points, score 0-100 | 3
| Visitor log | Save every visit and score | 0.5
| Challenge & block | Hidden check or block page | 2.5
| Pass score to order | Attach bot score to the order | 1
| Spy-tool check (optional) | Spot competitor spy extensions | 1
3. Fraud Check |  |  | 15
| New order trigger | Get order details when placed | 1.5
| Fraud list match | Known fraudster = high risk | 1
| Shopify risk | Use Shopify's own fraud rating | 1
| Warning signs | Email, IP, address, phone, order size | 2.5
| Bot score link | Suspicious browsing adds points | 0.5
| Fraud score | Add up points, decide action | 1
| Hold order | Stop shipping until reviewed | 1.5
| Auto-cancel | Cancel, refund, restock, email | 1.5
| Good signs | Loyal customers get lower score | 1.5
| Risky products | Limits on easy-to-resell items | 1
| Failed payments (optional) | Many declined cards adds points | 1
| Show in Shopify (optional) | Our verdict on Shopify order page | 1
4. Dashboard |  |  | 10.5
| Menu & pages | Basic app screens | 0.5
| Review queue | Held orders with approve/cancel | 3
| Bot activity | Blocked visitors with unblock | 1.5
| Settings | Change scores, limits, on/off | 2
| Overview | Today's numbers at a glance | 1.5
| Activity log | History of actions, with undo | 2
5. Fraud Tagging |  |  | 3.5
| Mark as fraud | Tag customer, save to fraud list | 1.5
| Catch returning fraudster | Flag their device next visit | 0.5
| Trust & fraud lists | Trust or remove customers | 1.5
6. Testing & Launch |  |  | 9
| Bot tests | Run fake bots against the store | 1.5
| Fraud tests | Place 5 test orders | 1.5
| Full story test | Run the whole example start to end | 1
| Go live | Put the app online | 2
| Fix bugs | Spare time for problems | 3
TOTAL |  |  | 56.5
Hours are hands-on hours building with Claude Code. Optional items can be skipped to save 3 hours.